## Post Completion Review
Post Completion Quantitative Review
Date:
Project Name
Project File:
Project Reference:
Society:
Occupancy Date:
Project Manager:
Procurement Method:
Attendees:
Capital Budget | PPA | COM | Variance | ACTUAL | Variance
|  |  | ( PPA - COM) |  | (COM - ACTUAL)
| 0 | 0 | 0 | 0 | 0
Brief Statement of why Change (If any) and lessons learned
Soft Costs | PPA | COM | Variance | ACTUAL | Variance
|  |  | ( PPA - COM) |  | (COM - ACTUAL)
| 0 | 0 | 0 | 0 | 0
Brief Statement of why Change (If any) and lessons learned
Common Furniture & Equip. | PPA | COM | Variance | ACTUAL | Variance
|  |  | ( PPA - COM) |  | (COM - ACTUAL)
| 0 | 0 | 0 | 0 | 0
Brief Statement of why Change (If any) and lessons learned
Contingency | PPA | COM | Variance | ACTUAL | Variance
|  |  | ( PPA - COM) |  | (COM - ACTUAL)
| 0 | 0 | 0 | 0 | 0
Brief Statement of why Change (If any) and lessons learned
Schedule | PPA | COM | Variance | ACTUAL | Variance
|  |  | ( PPA - COM) |  | (COM - ACTUAL)
Construction Start
Construction Complete
Brief Statement of why Change (If any) and lessons learned
Scope Changes | (i.e. Number of units, sustainability, building design):
Number of Units
Sustainability
Buiding Design
Brief Statement of why Change (If any) and lessons learned
CHANGE ORDERS
Total Number of Change Orders:
Total Value of Change Orders:
| Category 1 | Category 2 | Category 3 | Category 4 | Category 5
TOTALS for Building
Percentage of Each Category | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Percentage of Construction Contract
Brief Statement of major CO issues and lessons learned:
Post Completion Qualitative Review
|  | SUCCESSES |  | CHALLENGES
Project Communications
Roles and Responsibilities
Development Process
Design
Procurement
Construction
Schedule
Budget
Monitoring
Risk Management
Operational

## CO Log
Change Order Log
Project: |  |  |  | Owner: |  |  |  |  | Contractor:
BC Housing File/Reference No: |  |  |  | Address: |  |  |  |  | Contract Amount:
Category |  | Description |  | Total Contingency
1 |  | Existing Site Conditions |  | Capital Budget Variance
2 |  | Regulatory - Unforeseeable Requirements |  | Building CO's
3 |  | User Requests
4 |  | Project Improvements |  | Remaining Contingency |  | 0
5 |  | Consultant Team - ommitted from tender
6 |  | Consultant Team - Revision to an existing item
C/CO | # | Description | Amount (before HST) | Category 1 | Category 2 | Category 3 | Category 4 | Category 5 | Category 6 | Status | Approval Date
CO | 001
CO | 002
CO | 003
CO | 004
CO | 005
CO | 006
CO | 007
CD | 008
CO | 009
CO | 010
CO | 011
CO | 013
CO | 014
CO | 015
CO | 016
CO | 017
CO | 018
CO | 019
CO | 020
CO | 021
CO | 022
CO | 023
CO | 024
CO | 025
CO | 026
CO | 027
CO | 028
CO | 029
CO | 030
|  | TOTALS for Building | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Percentage of Each Category |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | Percentage of Construction Contract | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## Definitions
Definitions
Category 1. Existing Site Conditions
Changes caused by a response to existing site conditions encountered during construction. ( e.g. rock in service trench excavation)
Category 2: Regulatory: Unforeseeable Requirements
These changes are due to unforeseeable requirements by construction regulatory authorities during construction.
Category 3: User Requests
Changes due to design or scope revisions requested by the Users (i.e. the Society) during construction.
Category 4: Project Improvements
These changes are usually common sense responses to opportunities to improve the project during construction.
Category 5: Consultant Team: Omitted From Tender
These changes are due to items omitted from the tender scope of work. They may have been deliberately deleted and later added back due to changed circumstances.
Category 6: Consultant Team: Revision to an Existing Item
These are due to detail design revisions during construction.